## Task Sheet
Task ID | Task Name | Assigned To | Status | Start Date | End Date | Duration (work days) | % Complete | Depends On | Gate | Spec / SOP Ref | Blocked By | Notes
P0 | 0. Project initiation and SOP set-up
0.1 | Log idea in DS Projects - Master List; allocate ID 2026-40 | Chris | Complete | 2026-10-19 | 2026-10-19 | 1 | 100% |  |  | SOP 5 Stage 1 |  | ID 2026-40 in use across repo and docs
0.2 | Project brief issued (Feedback-Project-Brief) | Marc | Complete | 2026-10-19 | 2026-10-19 | 1 | 100% |  |  | Brief 2026-10-19 |  | Governs scope and architecture
0.3 | Draft Project Hub (sections 1-6) | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% | 0.2 |  | docs/project-hub.md |  | Ready to paste into Evernote template
0.4 | Set Master List status to Active | Chris | Not Started | 2026-10-22 | 2026-10-22 | 1 | 0% | 0.1 |  | SOP 4A |  | Only IT Director updates the Master List
0.5 | Create Evernote notebook; move and pin Project Hub note | Jacob Toledo | Not Started | 2026-10-22 | 2026-10-22 | 1 | 0% | 0.4 |  | SOP 5 Stage 2 step 1.1 |  | Space: DS Active and Proposed Projects
0.6 | Create Google Drive folder 2026-40 Feedback Desk | Jacob Toledo | Not Started | 2026-10-22 | 2026-10-22 | 1 | 0% | 0.4 |  | SOP 5 Stage 2 step 1.2 |  | Shared drive: DS Active and Proposed Projects
0.7 | Create Google Chat space 2026-40 Feedback Desk; add stakeholders | Jacob Toledo | Not Started | 2026-10-22 | 2026-10-22 | 1 | 0% | 0.4 |  | SOP 5 Stage 2 step 1.3 |  | Marc, Chris, Mike, Darlene, Mario
0.8 | Create Lucidchart folder; export diagrams to Drive | Jacob Toledo | Not Started | 2026-10-22 | 2026-10-22 | 1 | 0% | 0.4 |  | SOP 5 Stage 2 step 1.4
0.9 | Create this Smartsheet plan in DS Active Projects > 2026-40 Feedback Desk | Jacob Toledo | Not Started | 2026-10-22 | 2026-10-22 | 1 | 0% | 0.4 |  | SOP 5 Stage 2 step 2.1 |  | Import this file
0.10 | Glue systems: add all links to Hub; add Evernote link to README line 1 | Jacob Toledo | Not Started | 2026-10-23 | 2026-10-23 | 1 | 0% | 0.5, 0.6, 0.7, 0.8, 0.9 |  | SOP 4F, Stage 2 step 3 |  | README line 1 currently TODO
0.11 | Post pinned welcome message in Chat space | Jacob Toledo | Not Started | 2026-10-23 | 2026-10-23 | 1 | 0% | 0.10 |  | SOP 5 Stage 2 step 5
P1 | 1. Waiting on IT (Asks to Chris)
1.1 | Ask 1: Google Cloud projects (staging, production) under DS Projects | Chris | Blocked | 2026-10-19 | 2026-10-26 | 6 | 0% |  |  | Spec Asks 1; SOP 4G | Ask 1 | Display name 2026-40 Feedback Desk; GCP IDs must be lowercase, no underscores, start with a letter
1.2 | Ask 2: Google OAuth client for redadair.com.au | Chris | Blocked | 2026-10-19 | 2026-10-26 | 6 | 0% |  |  | Spec Asks 2 | Ask 2
1.3 | Ask 3: AI Studio key for Gemini | Chris | Complete | 2026-10-19 | 2026-10-21 | 3 | 100% |  |  | Spec Asks 3 |  | Arrived 21 Oct; move to Secret Manager once 1.1 lands
1.4 | Ask 4/10: Email provider (Gmail API or ZeptoMail) and sending domain | Chris | Blocked | 2026-10-19 | 2026-10-28 | 8 | 0% | 2.3 |  | Spec Asks 4, 10; D32 | Ask 4, 10
1.5 | Ask 5: Company GitHub repo 2026-40_Feedback_Desk with branch protection | Chris | Blocked | 2026-10-19 | 2026-10-26 | 6 | 0% |  |  | Spec Asks 5; SOP 4F; D27 | Ask 5 | Replaces temporary private repo
1.6 | Ask 6: Real Digital Staff list, triage lead, IT Admin | Chris | Not Started | 2026-10-19 | 2026-10-23 | 5 | 0% |  |  | Spec Asks 6; D20
1.7 | Ask 8: ~15 pilot staff and intranet tile slot | Chris | Not Started | 2026-10-26 | 2026-10-30 | 5 | 0% |  |  | Spec Asks 8
1.8 | Ask 9: Artifact Registry, Cloud SQL, buckets, service accounts, APIs | Chris | Blocked | 2026-10-19 | 2026-10-27 | 7 | 0% | 1.1 |  | Spec Asks 9 | Ask 9
P2 | 2. Decisions
2.1 | D31 PostgreSQL version (proposed 17) | Marc | Not Started | 2026-10-22 | 2026-10-23 | 2 | 0% |  |  | D31
2.2 | D36 Model and spend limits (proposed gemini-3.1-flash-lite) | Marc | Not Started | 2026-10-22 | 2026-10-23 | 2 | 0% |  |  | D36
2.3 | D32 Email provider (proposed ZeptoMail) | Marc | Not Started | 2026-10-22 | 2026-10-23 | 2 | 0% |  |  | D32
2.4 | D37 Smoke Signal brand and Sig assistant | Marc | Not Started | 2026-10-22 | 2026-10-23 | 2 | 0% |  |  | D37 |  | Show leadership before pilot
2.5 | D35 Production domain (e.g. feedback.redadair.com.au) | Chris | Not Started | 2026-10-22 | 2026-10-30 | 7 | 0% |  |  | D35
P3 | 3. Sprint 1: Foundations (gate: design review)
S1-1 | Repo, CI, Cloud Run YAML, deploy scripts, Docker Compose | Jacob Toledo | In Progress | 2026-10-20 | 2026-10-27 | 6 | 70% | 1.5 |  | S1-1 | Ask 5 | Written, not run
S1-2 | v3 data model, migrations, FB- sequence, seed | Jacob Toledo | Complete | 2026-10-20 | 2026-10-20 | 1 | 100% |  |  | S1-2
S1-3 | Google OAuth (redadair.com.au), roles server-side | Jacob Toledo | In Progress | 2026-10-20 | 2026-10-28 | 7 | 90% | 1.2 |  | S1-3 | Ask 2 | Built and tested with dev picker; test against Google once client exists
S1-4 | Admin page: projects, Digital Staff, routing rules | Jacob Toledo | Complete | 2026-10-20 | 2026-10-20 | 1 | 100% |  |  | S1-4
S1-5 | Design doc for review (architecture.md) | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S1-5
S1-6 | Rework v2 build to v3 | Jacob Toledo | Complete | 2026-10-20 | 2026-10-20 | 1 | 100% |  |  | S1-6
G1 | GATE 1: Design review signed by Marc and Chris | Marc | Not Started | 2026-10-23 | 2026-10-23 | 1 | 0% | S1-5 | Yes | Sprint 1 gate
P4 | 4. Sprint 2: Chatbot and agent (gate: routing 85%+)
S2-1 | Intake agent v3 (tools, schema, guardrails, PII masking) | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-1
S2-2 | Staff chat UI (streaming, chips, confirm card) | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-2
S2-3 | Attachments (type checks, macro rejection, Word/Excel text) | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-3 |  | Never slips
S2-4 | Router (confidence gate, rules, load balance, P1) | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-4 |  | Never slips
S2-5 | Developer brief with open gaps | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-5
S2-6 | Duplicate detection (embeddings, +1 and comment) | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-6
S2-7 | My feedback list and tracker page | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-7
S2-8 | Backup form when model fails | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-8
S2-9a | 40-item routing set and eval runner | Jacob Toledo | Complete | 2026-10-20 | 2026-10-21 | 2 | 100% |  |  | S2-9 |  | Gemini run 21 Oct: 97.5% project, 95% work type, 100% assignee
S2-9b | Marc reviews/extends labels; approves 85/85/80 thresholds | Marc | Not Started | 2026-10-22 | 2026-10-26 | 3 | 0% | S2-9a |  | S2-9; routing-eval-2026-10-21 |  | Add vague, wrong-tool and mixed items
S2-9c | Re-run eval 3x on approved set; record spread | Jacob Toledo | Not Started | 2026-10-26 | 2026-10-27 | 2 | 0% | S2-9b |  | routing-eval-2026-10-21
G2 | GATE 2: Routing gate signed by Marc and Chris | Marc | Not Started | 2026-10-27 | 2026-10-27 | 1 | 0% | S2-9c | Yes | Sprint 2 gate
P5 | 5. Sprint 3: Console (gate: UAT sign-off)
S3-1 | Board, List, Cards; filters; bulk actions | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% |  |  | S3-1
S3-2 | Detail panel | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% |  |  | S3-2
S3-3 | Approvals | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% |  |  | S3-3
S3-4 | Staff tracker (five stages) | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% |  |  | S3-4
S3-5 | Notifications (in-app SSE + email) | Jacob Toledo | In Progress | 2026-10-21 | 2026-10-28 | 6 | 80% | 1.4 |  | S3-5 | Ask 4/10 | Email via Mailpit locally; real provider pending D32
S3-6 | Project channels | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% |  |  | S3-6
S3-7 | Dashboard and daily digest | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% |  |  | S3-7 |  | First to slip; built
S3-8 | Deploy to staging and run post-deployment checks | Jacob Toledo | Not Started | 2026-10-27 | 2026-10-28 | 2 | 0% | 1.8, 1.5 |  | deployment.md; D25 | Asks 1, 5, 9
S3-9 | UAT walk-through of full lifecycle on staging | Marc | Not Started | 2026-10-29 | 2026-10-30 | 2 | 0% | S3-8 |  | Sprint 3 gate
G3 | GATE 3: UAT sign-off by Marc and Chris | Marc | Not Started | 2026-10-30 | 2026-10-30 | 1 | 0% | S3-9 | Yes | Sprint 3 gate
P6 | 6. Sprint 4: Pilot and launch (gate: go-live)
S4-1 | Friday release drafter, What's new | Jacob Toledo | Complete | 2026-10-21 | 2026-10-21 | 1 | 100% |  |  | S4-1 |  | AI rewording uses Gemini key
S4-2a | Production deploy: Cloud Run, Cloud SQL, Storage, Secret Manager; backups; alerting | Jacob Toledo | Not Started | 2026-11-02 | 2026-11-03 | 2 | 0% | G3 |  | S4-2; D29
S4-2b | Agent Engine deployment | Jacob Toledo | Not Started | 2026-11-02 | 2026-11-03 | 2 | 0% | S3-8 |  | S4-2; D7
S4-3 | 3-day pilot with ~15 staff; daily fixes | Jacob Toledo | Not Started | 2026-11-04 | 2026-11-06 | 3 | 0% | S4-2a, 1.7 |  | S4-3
S4-4 | Intranet tile, staff guide, console runbook | Jacob Toledo | Not Started | 2026-11-02 | 2026-11-04 | 3 | 0% | 2.5 |  | S4-4
G4 | GATE 4: Go-live signed by Marc and Chris | Chris | Not Started | 2026-11-06 | 2026-11-06 | 1 | 0% | S4-3, S4-4 | Yes | Sprint 4 gate |  | No P1 open
P7 | 7. Close-out (SOP section 6)
7.1 | Set Master List status to Completed | Chris | Not Started |  |  |  | 0% | G4 |  | SOP 6.1 |  | After 60-day success review
7.2 | Move Drive folder, Evernote notebook to Completed and Archived; archive Chat space | Jacob Toledo | Not Started |  |  |  | 0% | 7.1 |  | SOP 6.2-6.4

## Read Me
2026-40 Feedback Desk - Task Sheet
Prepared 21 Oct 2026 from the repo (spec v3 sprint plan, build status, routing eval, Project Hub draft) and file dates.
How dates were set
Completed rows use actual dates from the repo: spec v1 19 Oct, v2 20 Oct, v3 build tested by 21 Oct (AI-assisted coding).
Open rows are forecasts from 22 Oct. Most remaining work waits on IT asks (GCP, OAuth, repo, infra, email) and gate sign-offs, not coding. Move dates when asks land.
Importing to Smartsheet
1. In DS Active Projects, create folder '2026-40 Feedback Desk'.
2. File > Import > Microsoft Excel, choose this file, sheet 'Task Sheet', first row as column headers.
3. Name the sheet '2026-40 Feedback Desk - Task Sheet'.
4. Set Start/End as Date columns, Assigned To as Contact list, Status as Dropdown, % Complete as Percent.
5. Indent task rows under the grey phase rows (Task IDs starting with P) to restore the hierarchy.
6. Optional: turn on dependencies in Project Settings and convert 'Depends On' Task IDs to Predecessor row numbers.
Status values
Not Started, In Progress, Blocked (waiting on an IT ask), On Hold, Complete.
To confirm
Set-up rows 0.4 to 0.11 are Not Started: the Hub draft says no notebook, Drive folder, Chat space, Lucid folder, company repo or GCP project exists yet.
GCP project IDs allow only lowercase letters, digits and hyphens and must start with a letter, so use display name '2026-40 Feedback Desk' and an ID such as 'ds-2026-40-feedback-desk'.